## #PROJECTNAME#
project: | Arduino Radar
calculator: | Dick van Kalsbeek
date: | 2017-09-29
WBS id | predecessor | task | requirement level (MoSCoW) | developer | Risc | duration (plan) | duration (do) | reflection (check) | transfer (act)
1 |  | Connect all devices to breadboard | M | Tim | Cables could be wongly connected | 0.1
2 |  | Code a simple servo script | M | Damien |  | 0.15 | 0.15
3 |  | Code a simple sonar script | M | Damien |  | 0.15 | 0.3
4 |  | Code a simple steppermotor script | M | Damien |  | 0.3 | 0.3
5 |  | Compiler switches gebruiken | M | Damien |  | 0.5 | 0.5 | used switches for debug | makkelijk om code te deactiveren dat nog niet af is
6 |  | Serieel protocol op basis van C# eisen | M | Damien
7 |  | Interrupts toevoegen | M | Damien
8 |  | Data bewaren in EEPROM | M | Damien |  | 1 | 2
9 |  | Stepper/sonar aansturen gebaseerd op timer | M | Damien |  | 1 | 0.3 | Ik gebruikte een timer library
10 |  | Examenopdracht | M | Tim
12 |  | Configuration management | M | Damien | ??? Vragen
13 |  | Testplan document | M | Tim | Niet vaak gedaan
14 |  | Testresulaten document | M | Tim
15 |  | Maak gebruik van Port manipulation | M |  | Hoe? En wat
16 |  | EEPROM read/write test | M | Damien |  | 0.5 | 0.5
17 |  | Maak bitmask function | M | Damien |  | 1 | 0.5
18 |  | Test incrimentele encoder | M | Damien |  | 1 | 3
19 |  | Maak library voor encoder | M | Damien |  | 2 | 2 | Het was veel uitzoeken | Mijn libraries behouden voor referentie
|  | totaal |  |  |  | 7.7 | 9.55

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma